## Product Backlog
Product Backlog for New Payroll System
Task ID | User Story | Estimate (Story Points) | Priority
4 | As a user, I want to enter my work hours so I can make sure I get paid on time | 5 | 1 | Sprint 1
2 | As an administrator, I want to approve timesheets so employees get paid | 3 | 2
3 | As a user, I want to log in to the system so I can perform payroll functions | 3 | 3
1 | As a user, I want to log off of the system so no one can enter erroneous information in my account | 3 | 4
6 | As an administrator, I want to run consolidated payroll reports so I can provide a weekly status to senior management | 5 | 5
5 | As an administrator, I want the ability to create new accounts so we can add employees after they’re hired | 13 | 6 | Sprint 2
8 | As a user, I want the ability to edit my timesheet so I can correct any mistakes | 5 | 7
7 | As an administrator, I want the ability to set automated reminders so employees will verify and sign their timesheets on time | 8 | 8 | Sprint 3
9 | As an administrator, I want the ability to archive timesheets so the organization can file them for audit and tax purposes | 13 | 9
As a <User>
I want to do <Something>
So that I can achieve <Value>

## Sprint Backlog #1
4 | As a user, I want to enter my work hours so I can make sure I get paid on time |  | 5
TaskID | TaskDescription | Developer | Hours | MON | TUE | WED | THU | FRI
Task #1 |  | John | 8 | 6 | 4 | 0 | 0 | 0
Task #2 |  | Tim | 6 | 4 | 2 | 2 | 2 | 2 | DATE | ESTIMATED | MON | TUE | WED | THU | FRI
Task #3 |  | George | 8 | 8 | 8 | 6 | 4 | 2 | REMANING HOURS | 142 | 130 | 112 | 88 | 44 | 26
Task #4 |  |  | 4 | 4 | 4 | 2 | 0 | 0 | IDEAL TREND | 142 | 113.6 | 85.2 | 56.8 | 28.4 | 0
2 | As an administrator, I want to approve timesheets so employees get paid |  | 3
Task #5 |  |  | 8 | 8 | 6 | 6 | 4 | 4
Task #6 |  |  | 6 | 4 | 4 | 2 | 0 | 0
Task #7 |  |  | 8 | 6 | 4 | 4 | 2 | 0
Task #8 |  |  | 4 | 4 | 4 | 4 | 2 | 2
Task #9 |  |  | 4 | 4 | 4 | 4 | 2 | 2
Task #10 |  |  | 8 | 8 | 8 | 8 | 2 | 0
3 | As a user, I want to log in to the system so I can perform payroll functions |  | 3
Task#11 |  |  | 8 | 6 | 6 | 6 | 2 | 2
Task#12 |  |  | 6 | 4 | 4 | 2 | 2 | 0
Task#13 |  |  | 8 | 8 | 8 | 8 | 2 | 0
1 | As a user, I want to log off of the system so no one can enter erroneous information in my account |  | 3
Task #14 |  |  | 8 | 8 | 6 | 6 | 2 | 0
Task #15 |  |  | 6 | 6 | 4 | 4 | 4 | 4
Task #16 |  |  | 8 | 8 | 8 | 2 | 0 | 0
Task #17 |  |  | 8 | 8 | 6 | 6 | 2 | 0
6 | As an administrator, I want to run consolidated payroll reports so I can provide a weekly status to senior management |  | 5
Task #7 |  |  | 8 | 8 | 8 | 8 | 8 | 8
Task #8 |  |  | 8 | 8 | 4 | 4 | 2 | 0
Task #9 |  |  | 6 | 6 | 6 | 2 | 0 | 0
Task #10 |  |  | 4 | 4 | 4 | 2 | 2 | 0
| SUM |  | 142 | 130 | 112 | 88 | 44 | 26