## Sheet1
Weekly report
Your project title | Build Website Learning Japanese.(Online , Offline , Pay Course Advanced).
Platforms | Platform I will deploy your application Windows.
Frameworks | (Backend) Framework I will use for development is Codeigniter. Codeigniter like the laravel framework all uses the MVC model. Front-end (Framework I will use for development is Bootstrap 4)
Languages | Backend: Language I will use for development is PHP/MySQL. Front-End I will use HTML , CSS , Javascript.
Current progress | (60-70-80)%
Issues | I think the difficulty that I will have is a matter of time, because the very short time it takes to do a complete and fully functional project is very impossible.And the one problem I encountered was the course payment.
Code repository | https://github.com/luxurydemon123/final
Last week task | Done: Manage Admin ( Manage Slide , CRUD Slide HomePage . I used Json to mange Slide. Manage Student , Manage Teacher , Manager Gmail when somebody register course Offline). Part News . Admin can CRUD News and Category. Viewer Can View News and can not Edit. User Can login and logout . Admin can login/logout.
Next week task | Course detail. Manager Course (CRUD Lession , Category). Login with facebook. Gmail … Forgot password…